## RICs
Type | Cause | Effect | Impact | Likelihood | Importance | Response type | Response | Custodian | Dates
[9 empty] | Identification | Occurrence | Closure
R | Coding | Inefficient application and failures. Incorrect programming, being under pressure | 70 | 50 | 2 | Avoid | Testing and Adjust | JJ, RM, JB, JC, DB, DH
R | Joining coding elements between team members | Inefficient application and failures. Incorrect programming, being under pressure | 70 | 50 | 2 | Avoid | Testing and Adjust | JJ, RM, JB, JC, DB, DH
R | SQL Scripting errors | Inefficient application and failures. Incorrect programming, being under pressure | 70 | 50 | 2 | Avoid | Testing and Adjust | JJ, RM, JB, JC, DB, DH
R | Broken Object Level Authorization | Integrity of the site being compromised | 60 | 30 | 1 | Avoid | Testing and Adjust | JJ, RM, JB, JC, DB, DH
R | Broken User Authentication | Unauthorised access to the site | 50 | 30 | 1 | Avoid | Testing and Adjust | JJ, RM, JB, JC, DB, DH
R | Broken Function Level Authorization | Application failure | 40 | 30 | 1 | Avoid | Testing and Adjust | JJ, RM, JB, JC, DB, DH
R | Security Misconfiguration | Application security compromise | 40 | 30 | 1 | Avoid | Testing and Adjust | JJ, RM, JB, JC, DB, DH
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One of R = Risk I = Issue C = Change
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text to explain the source of the RIC
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text describing the effect of the RIC
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percentage rating of the impact of the risk on the project where 0 is negligible and 100 is disastrous.
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percentage rating of the likelihood of the risk where 0 is impossible and 100 is certain.
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value is calculated from impact and likelihood and colour-coded.
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One of Accept, Avoid, Mitigate, Transfer, Monitor
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short text describing the action planned (R) or taken (IC)
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Name of the person who is responsible for monitoring the RIC until it is closed
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC was identified
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC occurred
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date that the RIC was closed

## Profile
Impact
High | 0 | 3 | 0
Medium | 4 | 0 | 0
Low | 0 | 0 | 0
| Low | Medium | High | Likelihood

## Help
Help information |  |  | R | Accept
|  |  | I | Avoid
This file is used for recording and controlling risks, issues and changes (RICs) and should be reviewed and updated regularly. These terms are defined below. |  |  | C | Reduce
Transfer
Risk | A hypothetical event that might occur in the future and which would affect the project |  |  | Watch
Issue | An actual event that occurs and which requires some action to be taken
Change | A (potential) modification to the project definition after it has been finalised
Please refer to the notes below which described the contents of the fields on the main sheet.
Field | Required for | Description
Cause | RIC | Short text to explain the source of the RIC
Effect | RIC | Short text describing the effect of the RIC
Impact | R | Percentage rating of the impact of the risk on the project where 0 is negligible and 100 is disastrous.
Liklihood | R | Percentage rating of the likelihood of the risk where 0 is impossible and 100 is certain.
Significance | Calculated | This value is calculated from impact and likelihood and colour-coded
Response type | R | One of Accept, Avoid, Reduce, Transfer, Watch
Response | RIC | Short text describing the action planned (R) or taken (IC)
Custodian | RIC | Name of the person who is responsible for monitoring the RIC until it is closed
Identification | RIC | Date that the RIC was identified
Occurrence | RIC | Date that the RIC occurred
Closure | RIC | Date that the RIC was closed