## peer-review--project-initiation
Item	Score
Was a sponsor appointed to the project from the beginning?	80
Is the sponsor involved in high-level aspects of the project?	75
Does the sponsor avoid getting involved in the detail?	0
Was the project manager appointed to the project from the beginning?	100
Is the project manager familiar enough with P3.express?	60
Is there an effective setup for the project documents?	80
Are there enough key team members appointed to the project?	100
Were key team members actively involved in planning the project?	100
Is the Project Description well formed and useful?	80
Is the Deliverables Map well formed and useful?	100
Is the Follow-Up Register well formed and useful?	75

## peer-review--monthly
Item	w1	w2	w3	w4	w5	w6	w7	…
Was the plan for the upcoming month properly refined?
Is the high-level plan properly revised?
Is customer satisfaction evaluated properly?
Is team satisfaction evaluated properly?
Have we planned effective improvements?
Have we captured lessons learned?
Have we conducted effective focused communications?
Is the performance measurement reliable and useful?
Are the progress reports well formed and useful to their audience?
Have we collected feedback from the reports?
In the case of deviations, is there a proper recovery plan?
In the case of important deviations, was the sponsor involved in planning the response?
Did we have a proper kick-off events?
Did we manage risks, issues, and change requests properly and on a daily basis?
In the case of completed deliverables, have we checked and accepted them properly?

## peer-review--project-closure
Item	Score
Is the product approved and handed over?
In the case of remaining activities, are they clearly listed and approved?
Has customer satisfaction been evaluated and recorded?