## PROJECT DETAILS
PROJECT NUMBER | 13
PROJECT NAME | Men's Shed
PROJECT MANAGER | John Johnston
DATE | 2023-01-30
VERSION | 1

## WK 1 16-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Email/teams with prospective team members | Nil | Nil | Nil | 0.5
| What are doing today? | Nil | Nil | Nil | Nil | Nil
| Is there anything blocking you? | NIL | NIL | NIL | NIL | NIL
Jonathan | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil | Nil | Corresponding with potential team members | Nil | 0.2
| What are doing today? | Nil | Nil | Nil | Nil | Nil
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday?
What are doing today?
Is there anything blocking you?

## WK 2 23-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Nil | Nil | Nil | Nil | 5.45
| What are doing today? | Recruiting team members | Recruiting team members | Recruiting team members | Reading the Agile litirature | Reading the Agile litirature
| Is there anything blocking you? | Availability of different Course personel | Availability of different Course personel | Availability of different Course personel | Nil | Nil
Jonathan | What did you do yesterday? | [5 empty] | 1
| What are doing today? | Attended the Glassroom to search for a team placement, discussed potential to join Men's Shed Project
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil | Nil | Nil | Nil | 0.75
| What are doing today? | Nil | Nil | Contact team leader about project involvement | Nil | Looking over client brief, rewatching client presentation recording
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | [5 empty] | 0.25
| What are doing today? |  |  |  | Contacted team leader about prject involvement.
Is there anything blocking you?
Rory | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday?
What are doing today?
Is there anything blocking you?

## WK 3 30-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Message to the to consider several things for the initial meeting | Initial team meeting, introductions. Continuing Search for information on Agile project management. General correspondence. Client meeting request. | Searched for Documentation for the Project. IE Agile Documents | Client - Team communications. Confirm attendence at the Men's Shed Location | Client initial Meeting. Dunfermline. 4 hours | 5.45
| What are doing today? | Initial team meeting, introductions. Continuing Search for information on Agile project management. General correspondence. Client meeting request. | Searched for Documentation for the Project. IE Agile Documents | Client - Team communications. Confirm attendence at the Men's Shed Location | Client initial Meeting. Dunfermline. 4 hours | Initial feedback on the client meeting. Translating the meeting information into the foundation of the PIR ready for submission.
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Jonathan | What did you do yesterday? |  | Initial team meeting attended via Microsoft Teams |  |  | Attended initial meeting with the client at Dunfermline. | 5
| What are doing today? | Initial team meeting attended via Microsoft Teams |  |  | Attended initial meeting with the client at Dunfermline.
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0.3
| What are doing today? | Corresponding with team members regarding initial meeting | Nil | Nil | Nil | Contacting team members remotely
Is there anything blocking you?
Dainel | What did you do yesterday? | nil. |  |  |  |  | 1
| What are doing today? | Initial team meeting
| Is there anything blocking you? | nil.
Rory | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday?
What are doing today?
Is there anything blocking you?

## WK 4 06-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Team meeting, PIR report, and Communication with the team following the meeting. | PIR and team communication for report content | PIR and team communication for report content | Peer review for Group sound project. Completing PIR, Submit our PIR for peer review. Peer review edits from feedback | 4.45
| What are doing today? | Team meeting, PIR report, and Communication with the team following the meeting. | PIR and team communication for report content | PIR and team communication for report content | Peer review for Group sound project. Completing PIR, Submit our PIR for peer review. Peer review edits from feedback | Submit PIR to client, and for assessment
| Is there anything blocking you? | team contributions | team contributions | team contributions | team contributions | team contributions
Jonathan | What did you do yesterday? |  | Reviewed Initial PIR draft | Wrote security considerations of PIR report |  |  | 3.3
| What are doing today? | Reviewed Initial PIR draft | Wrote security considerations of PIR report |  | Produced a suggestion for the PIR report with slightly different formatting
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Team meeting, taking meeting minutes and setting up GitHub repository | Reading meeting minutes, begin my contribution to the report | Submitting my segment for the PIR, making necessary adjustments | Finalise contribution to PIR, deliver product timeline for front-end subteam | 4.3
| What are doing today? | Team meeting, taking meeting minutes and setting up GitHub repository | Reading meeting minutes, begin my contribution to the report | Submitting my segment for the PIR, making necessary adjustments | Finalise contribution to PIR, deliver product timeline for front-end subteam | Checking in with team regarding PIR
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | nil. |  | Nil. |  | nil. | 4
| What are doing today? | Set up trello board |  | Chat with Joe about what our segment on the PIR report |  | Trello board finalised and ready to share with team shared with the team
| Is there anything blocking you? | discussing with team to understand all tasks to be represented on the trello |  | Nil. |  | Nil.
Rory | What did you do yesterday? | [5 empty] | 3
| What are doing today? |  |  | Wrote my part of the PIR report
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 2
| What are doing today? |  | made my contrabutions to the PIR repot
Is there anything blocking you?

## WK 5 13-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Nil. | Nil. | Nil. | Nil. | 4.75
| What are doing today? | Lectures and Meetings. PM Forum. Emails to clients and course tutors | Further correspondence with client over server access using SSH. Not available so requested university development server for project. | nil |  | Emails to Brian and University tech team. Mondays Meeting Agenda.
| Is there anything blocking you? | Nil. | Nil. | Nil. | Nil. | Nil.
Jonathan | What did you do yesterday? | [5 empty] | 4
| What are doing today? | Lectures and team meeting. Taking minutes and adding files to GitHub |  |  |  | Working on an initial testing plan document
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil. | Nil | Nil. | Nil. | 6.25
| What are doing today? | Lectures and team meeting. Taking minutes and adding files to GitHub | Begin notes on wireframe design requirements | Front-End subteam meeting, discussing and beginning wireframe designs | Completing wireframe designs for each page, | Refining wireframes and completing daily scrum spreadsheet
| Is there anything blocking you? | Nil | Nil. | Nil | Nil. | Nil.
Dainel | What did you do yesterday? | Nil. | Nil. | Note taking | working on wireframes | Completing wireframes for each page | 6.25
| What are doing today? | Team meeting and shared Trello board with client | Notes and developing some wireframes | Met with Joe. shared initial ideas and created more wireframes | Working on wireframes | finished 5 wireframes and making adjustements based on Joe's wireframes
| Is there anything blocking you? | Nil. | Nil. | Desktop computer went down in JKCC for 15 minutes. | nil. | Nil.
Rory | What did you do yesterday? | [5 empty] | 2.5
| What are doing today? | Set up structured file package for code development |  |  |  | Set up virtual enviroment and a blank home page for webapp. Commited to github. Added comments.
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 1
| What are doing today? |  |  |  |  | writing sql files for the database
Is there anything blocking you?

## WK 6 20-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Updated the spreadsheets |  |  |  |  | 3
| What are doing today? | Communications with Course Lead ref Server Project meeting with team and weekly scrum. Appointed deputy while away for family issues. Some coaching of JC |  | Communication with Client |  | Communication with Course lead
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 1
| What are doing today? | Team meeting | Review meeting minutes in preparation for sub team meeting tomorrow | Sub team meeting | Made changes to HTML pages
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 6
| What are doing today? | Team meeting with group
Is there anything blocking you?
Dainel | What did you do yesterday? | Nil. |  | Nil. | Began writing HTML | Subserdised text | 6.25
| What are doing today? | Team meeting |  | Met with Joe. began writing html for website home page | Subserdised text and images that will be included in the webpages for easier use in development | Continue HTML
| Is there anything blocking you? | nil. |  | Lack of HTML knowledge | Nil. | Nil.
Rory | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 1.5
| What are doing today? |  | looking at changes to be made for SQLite | combined sqll files into one after forgeting upload the pervise files made for SQLite
Is there anything blocking you?

## WK 7 27-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 0.5
| What are doing today? | Discussion with Sponsor | Away | Away | Away | Away
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 3
| What are doing today? | Attended optional lecture to gather STARL information, team meeting |  |  | Researched how to implement bcrypt in a python flask application
Is there anything blocking you?
Joe | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | nil. | nil. | Refined resource page |  |  | 5
| What are doing today? | Team meeting | Talked with Joe with how the resource page should include features from each of our designs | Added more text to copy paste for easier development
| Is there anything blocking you? | nil. | nil. | Lack of knowledge on HTML development
Rory | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 2.5
| What are doing today? |  |  |  | looked in to how to displaying images in a database
| Is there anything blocking you? |  |  |  | the data base neededs to be rerun so no point enttering data that will be lost

## WK 8 06-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 2.25
| What are doing today? | Preparing meeting minutes, updating management spreadsheets emails to team Started the MID term report. Some coaching of JC regarding project management, following standing in while away! |  |  | Emails to client. | emails to client, Sponsor. Extension application
Is there anything blocking you?
Jonathan | What did you do yesterday? |  |  |  |  | Added Bcrypt initialisation to init.py in preparation for user login functionality | 2
| What are doing today? | Team meeting |  |  | Further research on bcrypt implementation, add initialisation for bcrypt. | Mid-point report security and testing section
| Is there anything blocking you? |  |  |  | Lack of knowledge on flask implementation
Joe | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 3
| What are doing today? |  |  |  | made the database done, not done and risks to the mid piont report | createded files to add data into the data base
Is there anything blocking you?

## WK 9 13-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Agena Spreadsheets |  |  |  |  | 5
| What are doing today? | Meeting , Minutes emails |  | emails and chat messages | Preporation for the Client meetingMeeting with Client
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 1
| What are doing today? | Team meeting
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?

## WK 9 20-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Agenda & Spreadsheets |  |  |  |  | 2.5
| What are doing today? | Meeting , Minutes emails
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?

## WK 9 27-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 2.5
What are doing today?
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?

## WK 9 03-04-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 2.5
What are doing today?
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0
What are doing today?
Is there anything blocking you?