## Status Report 13-02
Status Report Template
Project Information
Project Name |  | Men's Shed
Reporting Period |  | 26/01/23 - 13/02/23
Report Date |  | 2023-02-13
Project Manager |  | John Johnston
Project Sponsor |  | Iain Donald
Project Status Summary
Key Accomplishments
PIR Report |  |  | Access to Server, Trello and Stack mail
Peer Review |  |  | Development Started
Progress Report
Completed Work
Action Item | Date | RAG | Owner | Comments
Database | 2023-02-13 |  | DH, RM, DB, JB
Access to Server | 2023-02-14 |  | DH, RM, DB, JB | Advertised
PIR Report | 2023-02-10 |  | JJ, JC, DH, RM, DB, JB | Submitted minus Sponsor Feedback.
Peer Review | 2023-02-10 |  | JJ | Excellent feedback by independent PM
Upcoming Work
Action Item | Date | RAG | Owner | Comments
First Protatype | 2023-02-20 |  | DH, RM, DB, JB
Bcrypt Security | 2023-02-20 |  | DH, RM, DB, JB
Feedback Sponsor | 2023-02-13 |  | JJ, DB
Project Deliverables
Deliverable Description | Date | RAG | Owner | Comments
Database | 2023-02-20 |  | RM, DH
Basic Views | 2023-02-20 |  | RB, DB
UI Base | 2023-02-20 |  | RB, DB
Project Milestones
Milestone Description | Date | RAG | Owner | Comments
First Prototype | 2023-02-20 |  | JJ, JC, DH, RM, DB, JB
Project Health
Project Budget Overview
Budget Spent | % Spent | Notes |  | RAG
Project Schedule Overview
Action Item | RAG | Notes
Project Scope Overview
RAG |  | Notes
Quality Control & Assurance Overview
RAG |  | Notes
Risk Management Overview
Risk/Issue |  | Severity | Risk Response Action |  | Risk Owner
Conclusions & Recommendations

## SR 20-02
Status Report Template
Project Information
Project Name |  | Men's Shed
Reporting Period |  | 26/01/23 - 13/02/23
Report Date |  | 2023-02-13
Project Manager |  | John Johnston
Project Sponsor |  | Iain Donald
Project Status Summary
Key Accomplishments
PIR Report |  |  | Access to Server, Trello and Stack mail
Peer Review |  |  | Development Started
Progress Report
Completed Work
Action Item | Date | RAG | Owner | Comments
Database | 2023-02-13 |  | DH, RM, DB, JB
Access to Server | 2023-02-14 |  | DH, RM, DB, JB | Advertised
PIR Report | 2023-02-10 |  | JJ, JC, DH, RM, DB, JB | Submitted minus Sponsor Feedback.
Peer Review | 2023-02-10 |  | JJ | Excellent feedback by independent PM
Upcoming Work
Action Item | Date | RAG | Owner | Comments
First Protatype | 2023-02-20 |  | DH, RM, DB, JB
Bcrypt Security | 2023-02-20 |  | DH, RM, DB, JB
Feedback Sponsor | 2023-02-13 |  | JJ, DB
Project Deliverables
Deliverable Description | Date | RAG | Owner | Comments
Database | 2023-02-20 |  | RM, DH
Basic Views | 2023-02-20 |  | RB, DB
UI Base | 2023-02-20 |  | RB, DB
Project Milestones
Milestone Description | Date | RAG | Owner | Comments
First Prototype | 2023-02-20 |  | JJ, JC, DH, RM, DB, JB
Project Health
Project Budget Overview
Budget Spent | % Spent | Notes |  | RAG
Project Schedule Overview
Action Item | RAG | Notes
Project Scope Overview
RAG |  | Notes
Quality Control & Assurance Overview
RAG |  | Notes
Risk Management Overview
Risk/Issue |  | Severity | Risk Response Action |  | Risk Owner
Conclusions & Recommendations

## SR 27-02
Status Report Template
Project Information
Project Name |  | Men's Shed
Reporting Period |  | 26/01/23 - 13/02/23
Report Date |  | 2023-02-13
Project Manager |  | John Johnston
Project Sponsor |  | Iain Donald
Project Status Summary
Key Accomplishments
Progress Report
Completed Work
Action Item | Date | RAG | Owner | Comments
Upcoming Work
Action Item | Date | RAG | Owner | Comments
Project Deliverables
Deliverable Description | Date | RAG | Owner | Comments
Project Milestones
Milestone Description | Date | RAG | Owner | Comments
Project Health
Project Budget Overview
Budget Spent | % Spent | Notes |  | RAG
Project Schedule Overview
Action Item | RAG | Notes
Project Scope Overview
RAG |  | Notes
Quality Control & Assurance Overview
RAG |  | Notes
Risk Management Overview
Risk/Issue |  | Severity | Risk Response Action |  | Risk Owner
Conclusions & Recommendations

## SR 06-03
Status Report Template
Project Information
Project Name |  | Men's Shed
Reporting Period |  | 26/01/23 - 13/02/23
Report Date |  | 2023-02-13
Project Manager |  | John Johnston
Project Sponsor |  | Iain Donald
Project Status Summary
Key Accomplishments
Progress Report
Completed Work
Action Item | Date | RAG | Owner | Comments
Upcoming Work
Action Item | Date | RAG | Owner | Comments
Project Deliverables
Deliverable Description | Date | RAG | Owner | Comments
Project Milestones
Milestone Description | Date | RAG | Owner | Comments
Project Health
Project Budget Overview
Budget Spent | % Spent | Notes |  | RAG
Project Schedule Overview
Action Item | RAG | Notes
Project Scope Overview
RAG |  | Notes
Quality Control & Assurance Overview
RAG |  | Notes
Risk Management Overview
Risk/Issue |  | Severity | Risk Response Action |  | Risk Owner
Conclusions & Recommendations