## PROJECT DETAILS
PROJECT NUMBER | 13
PROJECT NAME | Men's Shed
PROJECT MANAGER | John Johnston
DATE | 2023-01-30
VERSION | 1

## WK 1 16-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Email/teams with prospective team members | Nil | Nil | Nil | 0.5 | 0.5 | 71.43% | 71.43%
| What are doing today? | Nil | Nil | Nil | Nil | Nil
| Is there anything blocking you? | NIL | NIL | NIL | NIL | NIL
Jonathan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil | Nil | Corresponding with potential team members | Nil | 0.2 | 0.2 | 28.57% | 28.57%
| What are doing today? | Nil | Nil | Nil | Nil | Nil
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 0.7 | 0.7 | 100% | 100%

## WK 2 23-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Nil | Nil | Nil | Nil | 5.45 | 5.95 | 73.15% | 73.01%
| What are doing today? | Recruiting team members | Recruiting team members | Recruiting team members | Reading the Agile litirature | Reading the Agile litirature
| Is there anything blocking you? | Availability of different Course personel | Availability of different Course personel | Availability of different Course personel | Nil | Nil
Jonathan | What did you do yesterday? | [5 empty] | 1 | 1 | 13.42% | 12.27%
| What are doing today? | Attended the Glassroom to search for a team placement, discussed potential to join Men's Shed Project
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil | Nil | Nil | Nil | 0.75 | 0.95 | 10.07% | 11.66%
| What are doing today? | Nil | Nil | Contact team leader about project involvement | Nil | Looking over client brief, rewatching client presentation recording
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | [5 empty] | 0.25 | 0.25 | 3.356% | 3.067%
| What are doing today? |  |  |  | Contacted team leader about prject involvement.
Is there anything blocking you?
Rory | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 7.45 | 8.15 | 100% | 100%

## WK 3 30-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Message to the to consider several things for the initial meeting | Initial team meeting, introductions. Continuing Search for information on Agile project management. General correspondence. Client meeting request. | Searched for Documentation for the Project. IE Agile Documents | Client - Team communications. Confirm attendence at the Men's Shed Location | Client initial Meeting. Dunfermline. 4 hours | 5.45 | 11.4 | 46.38% | 57.29%
| What are doing today? | Initial team meeting, introductions. Continuing Search for information on Agile project management. General correspondence. Client meeting request. | Searched for Documentation for the Project. IE Agile Documents | Client - Team communications. Confirm attendence at the Men's Shed Location | Client initial Meeting. Dunfermline. 4 hours | Initial feedback on the client meeting. Translating the meeting information into the foundation of the PIR ready for submission.
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Jonathan | What did you do yesterday? |  | Initial team meeting attended via Microsoft Teams |  |  | Attended initial meeting with the client at Dunfermline. | 5 | 6 | 42.55% | 30.15%
| What are doing today? | Initial team meeting attended via Microsoft Teams |  |  | Attended initial meeting with the client at Dunfermline.
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0.3 | 1.25 | 2.553% | 6.281%
| What are doing today? | Corresponding with team members regarding initial meeting | Nil | Nil | Nil | Contacting team members remotely
Is there anything blocking you?
Dainel | What did you do yesterday? | nil. |  |  |  |  | 1 | 1.25 | 8.511% | 6.281%
| What are doing today? | Initial team meeting
| Is there anything blocking you? | nil.
Rory | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 11.75 | 19.9 | 100% | 100%

## WK 4 06-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Team meeting, PIR report, and Communication with the team following the meeting. | PIR and team communication for report content | PIR and team communication for report content | Peer review for Group sound project. Completing PIR, Submit our PIR for peer review. Peer review edits from feedback | 4.45 | 15.85 | 21.14% | 38.71%
| What are doing today? | Team meeting, PIR report, and Communication with the team following the meeting. | PIR and team communication for report content | PIR and team communication for report content | Peer review for Group sound project. Completing PIR, Submit our PIR for peer review. Peer review edits from feedback | Submit PIR to client, and for assessment
| Is there anything blocking you? | team contributions | team contributions | team contributions | team contributions | team contributions
Jonathan | What did you do yesterday? |  | Reviewed Initial PIR draft | Wrote security considerations of PIR report |  |  | 3.3 | 9.3 | 15.68% | 22.71%
| What are doing today? | Reviewed Initial PIR draft | Wrote security considerations of PIR report |  | Produced a suggestion for the PIR report with slightly different formatting
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Team meeting, taking meeting minutes and setting up GitHub repository | Reading meeting minutes, begin my contribution to the report | Submitting my segment for the PIR, making necessary adjustments | Finalise contribution to PIR, deliver product timeline for front-end subteam | 4.3 | 5.55 | 20.43% | 13.55%
| What are doing today? | Team meeting, taking meeting minutes and setting up GitHub repository | Reading meeting minutes, begin my contribution to the report | Submitting my segment for the PIR, making necessary adjustments | Finalise contribution to PIR, deliver product timeline for front-end subteam | Checking in with team regarding PIR
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | nil. |  | Nil. |  | nil. | 4 | 5.25 | 19% | 12.82%
| What are doing today? | Set up trello board |  | Chat with Joe about what our segment on the PIR report |  | Trello board finalised and ready to share with team shared with the team
| Is there anything blocking you? | discussing with team to understand all tasks to be represented on the trello |  | Nil. |  | Nil.
Rory | What did you do yesterday? | [5 empty] | 3 | 3 | 14.25% | 7.326%
| What are doing today? |  |  | Wrote my part of the PIR report
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 2 | 2 | 9.501% | 4.884%
| What are doing today? |  | made my contrabutions to the PIR repot
Is there anything blocking you?
[7 empty] | 21.05 | 40.95 | 100% | 100%

## WK 5 13-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Nil. | Nil. | Nil. | Nil. | 4.75 | 20.6 | 19.19% | 31.35%
| What are doing today? | Lectures and Meetings. PM Forum. Emails to clients and course tutors | Further correspondence with client over server access using SSH. Not available so requested university development server for project. | nil |  | Emails to Brian and University tech team. Mondays Meeting Agenda.
| Is there anything blocking you? | Nil. | Nil. | Nil. | Nil. | Nil.
Jonathan | What did you do yesterday? | [5 empty] | 4 | 13.3 | 16.16% | 20.24%
| What are doing today? | Lectures and team meeting. Taking minutes and adding files to GitHub |  |  |  | Working on an initial testing plan document
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil. | Nil | Nil. | Nil. | 6.25 | 11.8 | 25.25% | 17.96%
| What are doing today? | Lectures and team meeting. Taking minutes and adding files to GitHub | Begin notes on wireframe design requirements | Front-End subteam meeting, discussing and beginning wireframe designs | Completing wireframe designs for each page, | Refining wireframes and completing daily scrum spreadsheet
| Is there anything blocking you? | Nil | Nil. | Nil | Nil. | Nil.
Dainel | What did you do yesterday? | Nil. | Nil. | Note taking | working on wireframes | Completing wireframes for each page | 6.25 | 11.5 | 25.25% | 17.5%
| What are doing today? | Team meeting and shared Trello board with client | Notes and developing some wireframes | Met with Joe. shared initial ideas and created more wireframes | Working on wireframes | finished 5 wireframes and making adjustements based on Joe's wireframes
| Is there anything blocking you? | Nil. | Nil. | Desktop computer went down in JKCC for 15 minutes. | nil. | Nil.
Rory | What did you do yesterday? | [5 empty] | 2.5 | 5.5 | 10.1% | 8.371%
| What are doing today? | Set up structured file package for code development |  |  |  | Set up virtual enviroment and a blank home page for webapp. Commited to github. Added comments.
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 1 | 3 | 4.04% | 4.566%
| What are doing today? |  |  |  |  | writing sql files for the database
Is there anything blocking you?
[7 empty] | 24.75 | 65.7 | 100% | 100%

## WK 6 20-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Updated the spreadsheets |  |  |  |  | 3 | 23.6 | 11.65% | 25.81%
| What are doing today? | Communications with Course Lead ref Server Project meeting with team and weekly scrum. Appointed deputy while away for family issues. Some coaching of JC |  | Communication with Client |  | Communication with Course lead
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 1 | 14.3 | 3.883% | 15.64%
| What are doing today? | Team meeting | Review meeting minutes in preparation for sub team meeting tomorrow | Sub team meeting | Made changes to HTML pages
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 6 | 17.8 | 23.3% | 19.46%
| What are doing today? | Team meeting with group
Is there anything blocking you?
Dainel | What did you do yesterday? | Nil. |  | Nil. | Began writing HTML | Subserdised text | 6.25 | 17.75 | 24.27% | 19.41%
| What are doing today? | Team meeting |  | Met with Joe. began writing html for website home page | Subserdised text and images that will be included in the webpages for easier use in development | Continue HTML
| Is there anything blocking you? | nil. |  | Lack of HTML knowledge | Nil. | Nil.
Rory | What did you do yesterday? | [5 empty] | 8 | 13.5 | 31.07% | 14.76%
| What are doing today? |  |  | set up database
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 1.5 | 4.5 | 5.825% | 4.921%
| What are doing today? |  | looking at changes to be made for SQLite | combined sqll files into one after forgeting upload the pervise files made for SQLite
Is there anything blocking you?
[7 empty] | 25.75 | 91.45 | 100 | 100%

## WK 7 27-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 0.5 | 24.1 | 5% | 23.76%
| What are doing today? | Discussion with Sponsor | Away | Away | Away | Away
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 3 | 17.3 | 30% | 17.05%
| What are doing today? | Attended optional lecture to gather STARL information, team meeting |  |  | Researched how to implement bcrypt in a python flask application
Is there anything blocking you?
Joe | What did you do yesterday? | [6 empty] | 17.8 | 0% | 17.55%
| What are doing today? | Team meeting, meeting minutes | Discussed page designs with Daniel | Sub team meeting, implementation of page designs
Is there anything blocking you?
Dainel | What did you do yesterday? | nil. | nil. | Refined resource page |  |  | 4 | 21.75 | 40% | 21.44%
| What are doing today? | Team meeting | Talked with Joe with how the resource page should include features from each of our designs | Added more text to copy paste for easier development
| Is there anything blocking you? | nil. | nil. | Lack of knowledge on HTML development
Rory | What did you do yesterday? | [6 empty] | 13.5 | 0% | 13.31%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 2.5 | 7 | 25% | 6.9%
| What are doing today? |  |  |  | looked in to how to displaying images in a database
| Is there anything blocking you? |  |  |  | the data base neededs to be rerun so no point enttering data that will be lost
[7 empty] | 10 | 101.45 | 100% | 100%

## WK 8 06-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 2.25 | 26.35 | 19.15% | 23.28%
| What are doing today? | Preparing meeting minutes, updating management spreadsheets emails to team Started the MID term report. Some coaching of JC regarding project management, following standing in while away! |  |  | Emails to client. | emails to client, Sponsor. Extension application
Is there anything blocking you?
Jonathan | What did you do yesterday? |  |  |  |  | Added Bcrypt initialisation to init.py in preparation for user login functionality | 2 | 19.3 | 17.02% | 17.05%
| What are doing today? | Team meeting |  |  | Further research on bcrypt implementation, add initialisation for bcrypt. | Mid-point report security and testing section
| Is there anything blocking you? |  |  |  | Lack of knowledge on flask implementation
Joe | What did you do yesterday? | [5 empty] | 4.5 | 22.3 | 38.3% | 19.7%
| What are doing today? | Team meeting, taking minutes for meeting |  | Gathering evidence for STARL example draft | Editing and formatting STARL draft for Friday | Submitting STARL draft
| Is there anything blocking you? |  |  |  |  | Unable to attend classes due to illness
Dainel | What did you do yesterday? | [6 empty] | 21.75 | 0% | 19.21%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [6 empty] | 13.5 | 0% | 11.93%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 3 | 10 | 25.53% | 8.834%
| What are doing today? |  |  |  | made the database done, not done and risks to the mid piont report | createded files to add data into the data base
Is there anything blocking you?
[7 empty] | 11.75 | 113.2 | 100% | 100%

## WK 9 13-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Agena Spreadsheets |  |  |  |  | 5 | 31.35 | 55.56% | 25.65%
| What are doing today? | Meeting , Minutes emails |  | emails and chat messages | Preporation for the Client meetingMeeting with Client
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 1 | 20.3 | 11.11% | 16.61%
| What are doing today? | Team meeting
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 3 | 25.3 | 33.33% | 20.7%
| What are doing today? | Checking in with team virtually regarding next steps |  | Working on STARL example and uploading evidence | Team meeting with client | Discussion with team regarding client's comments
| Is there anything blocking you? | Unable to attend classes due to illness
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 17.8%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 0 | 13.5 | 0% | 11.05%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 8.183%
What are doing today?
Is there anything blocking you?
[7 empty] | 9 | 122.2 | 100% | 100%

## WK 10 20-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Agenda & Spreadsheets |  |  |  |  | 2.5 | 28.85 | 14.29% | 22.07%
| What are doing today? | Meeting , Minutes emails
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 1 | 20.3 | 5.714% | 15.53%
| What are doing today? | Team meeting
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 22.3 | 0% | 17.06%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 16.64%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 14 | 27.5 | 80% | 21.04%
| What are doing today? |  |  | Worked on register and Login fetures | Got register and login features working
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 7.651%
What are doing today?
Is there anything blocking you?
[7 empty] | 17.5 | 130.7 | 100% | 100%

## WK 11 27-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 2.5 | 28.85 | 10.64% | 21.1%
| What are doing today? | Team meeting with the team and updating the tables |  |  | an email with the module lead and the client
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 1 | 20.3 | 4.255% | 14.85%
| What are doing today? | Team meeting
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 22.3 | 0% | 16.31%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 15.91%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 20 | 33.5 | 85.11% | 24.51%
| What are doing today? |  |  | Worked on booking feature prototype | Continued working on Booking prototype | Finished the bokking feature prototype
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 7.315%
What are doing today?
Is there anything blocking you?
[7 empty] | 23.5 | 136.7 | 100% | 100%

## WK 12 03-04-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 0.5 | 26.85 | 2.439% | 20.08%
| What are doing today? | unavailable | unavailable | unavailable | unavailable | emails with the client and the press office
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0 | 19.3 | 0% | 14.44%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 22.3 | 0% | 16.68%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 16.27%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 20 | 33.5 | 97.56% | 25.06%
| What are doing today? |  |  |  | Worked on Booking feature prototype and got it working better | Finshed Booking prototype and got it working correctly. Implemented Admin access functionality
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 7.479%
What are doing today?
Is there anything blocking you?
[7 empty] | 20.5 | 133.7 | 100% | 100%

## WK 13 10-04-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 0 | 26.35 | 0% | 19.78%
| What are doing today? | unavailable | unavailable | unavailable | unavailable | unavailable
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0 | 19.3 | 0% | 14.49%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 22.3 | 0% | 16.74%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 16.33%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 20 | 33.5 | 100% | 25.15%
| What are doing today? |  |  | Worked on booking feature prototype | Continued working on Booking prototype | Finished the bokking feature prototype
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 7.508%
What are doing today?
Is there anything blocking you?
[7 empty] | 20 | 133.2 | 100% | 100%

## WK 14 17-04-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 3 | 29.35 | 12.5% | 21.39%
| What are doing today? | Meeting with the team. Emails to the press office and the module lead |  |  |  | spreadsheet updates. Peer review for group 49 agenda for monda meeting. And emails to the team.
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 1 | 20.3 | 4.167% | 14.8%
| What are doing today? | Team meeting
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 22.3 | 0% | 16.25%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 15.85%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 20 | 33.5 | 83.33% | 24.42%
| What are doing today? |  |  | Worked on booking feature prototype | Continued working on Booking prototype | Finished the bokking feature prototype
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 7.289%
What are doing today?
Is there anything blocking you?
[7 empty] | 24 | 137.2 | 100% | 100%

## WK15 24-04-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 2.5 | 28.85 | 11.11% | 21.26%
What are doing today?
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0 | 19.3 | 0% | 14.22%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 22.3 | 0% | 16.43%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 16.03%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 20 | 33.5 | 88.89% | 24.69%
| What are doing today? |  |  | Worked on booking feature prototype | Continued working on Booking prototype | Finished the bokking feature prototype
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 7.369%
What are doing today?
Is there anything blocking you?
[7 empty] | 22.5 | 135.7 | 100% | 100%

## WK16 01-05-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 2.5 | 28.85 | 11.11% | 21.26%
What are doing today?
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0 | 19.3 | 0% | 14.22%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 22.3 | 0% | 16.43%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 21.75 | 0% | 16.03%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 20 | 33.5 | 88.89% | 24.69%
| What are doing today? |  |  | Worked on booking feature prototype | Continued working on Booking prototype | Finished the bokking feature prototype
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 10 | 0% | 7.369%
What are doing today?
Is there anything blocking you?
[7 empty] | 22.5 | 135.7 | 100% | 100%