## PROJECT DETAILS
PROJECT NUMBER | 13
PROJECT NAME | Men's Shed
PROJECT MANAGER | John Johnston
DATE | 2023-01-30
VERSION | 1

## WK 1 16-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Email/teams with prospective team members | Nil | Nil | Nil | 0.5 | 0.5 | 71.43% | 71.43%
| What are doing today? | Nil | Nil | Nil | Nil | Nil
| Is there anything blocking you? | NIL | NIL | NIL | NIL | NIL
Jonathan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil | Nil | Corresponding with potential team members | Nil | 0.2 | 0.2 | 28.57% | 28.57%
| What are doing today? | Nil | Nil | Nil | Nil | Nil
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 0.7 | 0.7 | 100% | 100%

## WK 2 23-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Nil | Nil | Nil | Nil | 5.45 | 5.95 | 84.5% | 83.22%
| What are doing today? | Recruiting team members | Recruiting team members | Recruiting team members | Reading the Agile litirature | Reading the Agile litirature
| Is there anything blocking you? | Availability of different Course personel | Availability of different Course personel | Availability of different Course personel | Nil | Nil
Jonathan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil | Nil | Nil | Nil | 0.75 | 0.95 | 11.63% | 13.29%
| What are doing today? | Nil | Nil | Contact team leader about project involvement | Nil | Looking over client brief, rewatching client presentation recording
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | [5 empty] | 0.25 | 0.25 | 3.876% | 3.497%
| What are doing today? |  |  |  | Contacted team leader about prject involvement.
Is there anything blocking you?
Rory | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 6.45 | 7.15 | 100% | 100%

## WK 3 30-01-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Message to the to consider several things for the initial meeting | Initial team meeting, introductions. Continuing Search for information on Agile project management. General correspondence. Client meeting request. | Searched for Documentation for the Project. IE Agile Documents | Client - Team communications. Confirm attendence at the Men's Shed Location | Client initial Meeting. Dunfermline. 4 hours | 5.45 | 11.4 | 46.38% | 60.32%
| What are doing today? | Initial team meeting, introductions. Continuing Search for information on Agile project management. General correspondence. Client meeting request. | Searched for Documentation for the Project. IE Agile Documents | Client - Team communications. Confirm attendence at the Men's Shed Location | Client initial Meeting. Dunfermline. 4 hours | Initial feedback on the client meeting. Translating the meeting information into the foundation of the PIR ready for submission.
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Jonathan | What did you do yesterday? |  | Initial team meeting attended via Microsoft Teams |  |  | Attended initial meeting with the client at Dunfermline. | 5 | 5 | 42.55% | 26.46%
| What are doing today? | Initial team meeting attended via Microsoft Teams |  |  | Attended initial meeting with the client at Dunfermline.
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0.3 | 1.25 | 2.553% | 6.614%
| What are doing today? | Corresponding with team members regarding initial meeting | Nil | Nil | Nil | Contacting team members remotely
Is there anything blocking you?
Dainel | What did you do yesterday? | nil. |  |  |  |  | 1 | 1.25 | 8.511% | 6.614%
| What are doing today? | Initial team meeting
| Is there anything blocking you? | nil.
Rory | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 11.75 | 18.9 | 100% | 100%

## WK 4 06-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Team meeting, PIR report, and Communication with the team following the meeting. | PIR and team communication for report content | PIR and team communication for report content | Peer review for Group sound project. Completing PIR, Submit our PIR for peer review. Peer review edits from feedback | 4.45 | 15.85 | 23.36% | 41.77%
| What are doing today? | Team meeting, PIR report, and Communication with the team following the meeting. | PIR and team communication for report content | PIR and team communication for report content | Peer review for Group sound project. Completing PIR, Submit our PIR for peer review. Peer review edits from feedback | Submit PIR to client, and for assessment
| Is there anything blocking you? | team contributions | team contributions | team contributions | team contributions | team contributions
Jonathan | What did you do yesterday? |  | Reviewed Initial PIR draft | Wrote security considerations of PIR report |  |  | 3.3 | 8.3 | 17.32% | 21.87%
| What are doing today? | Reviewed Initial PIR draft | Wrote security considerations of PIR report |  | Produced a suggestion for the PIR report with slightly different formatting
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Team meeting, taking meeting minutes and setting up GitHub repository | Reading meeting minutes, begin my contribution to the report | Submitting my segment for the PIR, making necessary adjustments | Finalise contribution to PIR, deliver product timeline for front-end subteam | 4.3 | 5.55 | 22.57% | 14.62%
| What are doing today? | Team meeting, taking meeting minutes and setting up GitHub repository | Reading meeting minutes, begin my contribution to the report | Submitting my segment for the PIR, making necessary adjustments | Finalise contribution to PIR, deliver product timeline for front-end subteam | Checking in with team regarding PIR
| Is there anything blocking you? | Nil | Nil | Nil | Nil | Nil
Dainel | What did you do yesterday? | nil. |  | Nil. |  | nil. | 4 | 5.25 | 21% | 13.83%
| What are doing today? | Set up trello board |  | Chat with Joe about what our segment on the PIR report |  | Trello board finalised and ready to share with team shared with the team
| Is there anything blocking you? | discussing with team to understand all tasks to be represented on the trello |  | Nil. |  | Nil.
Rory | What did you do yesterday? | [5 empty] | 3 | 3 | 15.75% | 7.905%
| What are doing today? |  |  | Wrote my part of the PIR report
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 19.05 | 37.95 | 100% | 100%

## WK 5 13-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Nil | Nil. | Nil. | Nil. | Nil. | 4.75 | 20.6 | 21.84% | 34.51%
| What are doing today? | Lectures and Meetings. PM Forum. Emails to clients and course tutors | Further correspondence with client over server access using SSH. Not available so requested university development server for project. | nil |  | Emails to Brian and University tech team. Mondays Meeting Agenda.
| Is there anything blocking you? | Nil. | Nil. | Nil. | Nil. | Nil.
Jonathan | What did you do yesterday? | [5 empty] | 2 | 10.3 | 9.195% | 17.25%
| What are doing today? |  |  |  |  | Working on an initial testing plan document
Is there anything blocking you?
Joe | What did you do yesterday? | Nil | Nil. | Nil | Nil. | Nil. | 6.25 | 11.8 | 28.74% | 19.77%
| What are doing today? | Lectures and team meeting. Taking minutes and adding files to GitHub | Begin notes on wireframe design requirements | Front-End subteam meeting, discussing and beginning wireframe designs | Completing wireframe designs for each page, | Refining wireframes and completing daily scrum spreadsheet
| Is there anything blocking you? | Nil | Nil. | Nil | Nil. | Nil.
Dainel | What did you do yesterday? | Nil. | Nil. | Note taking | working on wireframes | Completing wireframes for each page | 6.25 | 11.5 | 28.74% | 19.26%
| What are doing today? | Team meeting and shared Trello board with client | Notes and developing some wireframes | Met with Joe. shared initial ideas and created more wireframes | Working on wireframes | finished 5 wireframes and making adjustements based on Joe's wireframes
| Is there anything blocking you? | Nil. | Nil. | Desktop computer went down in JKCC for 15 minutes. | nil. | Nil.
Rory | What did you do yesterday? | [5 empty] | 2.5 | 5.5 | 11.49% | 9.213%
| What are doing today? | Set up structured file package for code development |  |  |  | Set up virtual enviroment and a blank home page for webapp. Commited to github. Added comments.
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 21.75 | 59.7 | 100% | 100%

## WK 6 20-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | Updated the spreadsheets |  |  |  |  | 4 | 24.6 | 39.02% | 35.17%
| What are doing today? | Communications with Course Lead ref Server Project meeting with team and weekly scrum. Appointed deputy while away for family issues. Some coaching of JC |  | Communication with Client |  | Communication with Course lead
Is there anything blocking you?
Jonathan | What did you do yesterday? | [6 empty] | 10.3 | 0% | 14.72%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [6 empty] | 11.8 | 0% | 16.87%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | Nil. |  | Nil. | Began writing HTML | Subserdised text | 6.25 | 17.75 | 60.98% | 25.38%
| What are doing today? | Team meeting |  | Met with Joe. began writing html for website home page | Subserdised text and images that will be included in the webpages for easier use in development | Continue HTML
| Is there anything blocking you? | nil. |  | Lack of HTML knowledge | Nil. | Nil.
Rory | What did you do yesterday? | [6 empty] | 5.5 | 0% | 7.863%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 10.25 | 69.95 | 100 | 100%

## WK 7 27-02-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 0.5 | 25.1 | 9.091% | 33.27%
| What are doing today? | Discussion with Sponsor | Away | Away | Away | Away
Is there anything blocking you?
Jonathan | What did you do yesterday? | [6 empty] | 10.3 | 0% | 13.65%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [6 empty] | 11.8 | 0% | 15.64%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | nil. | nil. | Refined resource page |  |  | 5 | 22.75 | 90.91% | 30.15%
| What are doing today? | Team meeting | Talked with Joe with how the resource page should include features from each of our designs | Added more text to copy paste for easier development
| Is there anything blocking you? | nil. | nil. | Lack of knowledge on HTML development
Rory | What did you do yesterday? | [6 empty] | 5.5 | 0% | 7.29%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0% | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 5.5 | 75.45 | 100% | 100%

## WK 8 06-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 4.5 | 29.6 | 100% | 37.02%
| What are doing today? | Preparing meeting minutes, updating management spreadsheets emails to team Started the MID term report. Some coaching of JC regarding project management, following standing in while away!
Is there anything blocking you?
Jonathan | What did you do yesterday? | [6 empty] | 10.3 | 0 | 12.88%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [6 empty] | 11.8 | 0 | 14.76%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [6 empty] | 22.75 | 0 | 28.46%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [6 empty] | 5.5 | 0 | 6.879%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [6 empty] | 0 | 0 | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 4.5 | 79.95 | 1 | 100%

## WK 9 13-03-23
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday | Time | Running total
John | What did you do yesterday? | [5 empty] | 0 | 29.6 | #DIV/0! | 37.02%
What are doing today?
Is there anything blocking you?
Jonathan | What did you do yesterday? | [5 empty] | 0 | 10.3 | #DIV/0! | 12.88%
What are doing today?
Is there anything blocking you?
Joe | What did you do yesterday? | [5 empty] | 0 | 11.8 | #DIV/0! | 14.76%
What are doing today?
Is there anything blocking you?
Dainel | What did you do yesterday? | [5 empty] | 0 | 22.75 | #DIV/0! | 28.46%
What are doing today?
Is there anything blocking you?
Rory | What did you do yesterday? | [5 empty] | 0 | 5.5 | #DIV/0! | 6.879%
What are doing today?
Is there anything blocking you?
Duncan | What did you do yesterday? | [5 empty] | 0 | 0 | #DIV/0! | 0%
What are doing today?
Is there anything blocking you?
[7 empty] | 0 | 79.95 | #DIV/0! | 100%